## Sheet1
Falcon: the Gym Pro Assistant
Tasks |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
| Progress | 8/31 | 9/7 | 9/14 | 9/21 | 9/28 | 10/5 | 10/12 | 10/19 | 10/26 | 11/2 | 11/9 | 11/16 | 11/23 | 11/30 | 12/7 | 12/14
Milestones |  | Week 1: Project Planning; Week 4: Design Implementation; Week 10: Integration and Verification; Week 14: Project Report and Presentation
Signal Processing
Pre-processing image | 100% | bar: Week 4
Learn algorithm to extract joints | 100% | bar: Week 4
Implementing algorithm to extract joints (Python to C) | 100% | bar: Week 5
Refining the HSV Bounds | 100% | Week 7: 20%; Week 8: 60%; Week 9: 90%; Week 10: 100%
Implementing Posture Analysis | 100% | bar: Week 6 to Week 7
Determine thresholds for posture analysis | 80% | Week 8: 30%; Week 9: 65%; Week 10: 80%
Hardware | [17 empty] | Vishal
Learn Vivado/HLS | 100% | [16 empty] | Venkata | bar: Week 7 to Week 8
Convert joints algorithm to FPGA code | 100% | [16 empty] | Albert | bar: Week 8 to Week 10
Optimize algorithm for better performance | 0% | [16 empty] | Everyone | bar: Week 11 to Week 12
Learn communication protocol (UART) | 100% | bar: Week 4 to Week 5
Learn MicroBlaze/Vitis | 100% | bar: Week 8 to Week 9
Set up FPGA/Vivado | 100% | bar: Week 4 to Week 5
Implement communication protocol logic | 100% | bar: Week 5 to Week 6
Software + UI
Design the UI Model | 100% | bar: Week 4
Setup PyGame (Basic Framework) | 100% | bar: Week 5
Implement Camera Display + Capture Image | 100% | bar: Week 6
Integrate Recorded Model Exercise | 100% | bar: Week 6
Customize User Biodata and Create timed workout | 80% | bar: Week 7
Calories/Heart Rate Calculations | 100% | bar: Week 8
Learn/Implement Basic Threading | 100% | bar: Week 9
Output Feedback | 100% | bar: Week 10
Workout Summary | 80% | bar: Week 10 to Week 11
Initialize and Store Summaries/Biodata in Database | 30% | bar: Week 10 to Week 11
UI To View Workout History | 0% | bar: Week 12
Switch Profiles (Extra Feature) | 0% | bar: Week 13
Refining Implementation (Transitions between States/Pages) | 70% | bar: Week 11 to Week 13
Extraneous Setup
Create the Trackers | 100% | bar: Week 4 to Week 5
Integration + Final Verification
Verification of individual parts | 50% | bar: Week 10 to Week 11
Integrate + Verify I/O with Image Processing | 100% | bar: Week 10
Integrate + Verify processing output with UI | 100% | bar: Week 11 to Week 12
Integrate + Verify UART w/ UI (Synchronized) | 80% | bar: Week 11 to Week 12
Refining App and Integration | 50% | bar: Week 13 to Week 14
Proposal/Report/Presentation
Project Ideas | 100% | bar: Week 1 to Week 2
Abstract | 100% | Week 3: DUE
Project Proposal | 100% | Week 4: DUE
Design Presentation | 100% | Week 7: DUE
Design Report | 100% | Week 8: DUE
Demo in Lab | 100% | Week 11: DUE
In Lab Demo | 100% | Week 14: DUE
Final Presentation | 0% | Week 15: DUE
Final Report | 0% | Week 16: DUE
Note on A35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Show's feedback but not synchronized (todo in integration section)
Note on A51: Vishal Baskar: Need to make sure the Feedback shows up at correct time, rather than just terminal